## Sheet1
Change | Reason | Risk management | Agreement Date
add user management into milestone1 | To avoid editing foreign keys frequently later | learn how to encrypt password | 2023-04-02
add a new table 'logs' in database | to track every change(including editing) of borrowing requests | build an extra web-page 'action history' | 2023-04-06
split requests table into requests and borrows tables | for agile management, borrow-processes could be individual products | review existing APIs | 2023-04-08
remove unnecessary foreign keys | borrowing records can exist without type_id remained(could be deleted after returned) | review existing 'new borrowing' api endpoint, to limit only existing type_id can be borrowed | 2023-04-20
generate borrowing and equipment_log records with the origional borrow_amount, not spliting them into several records with borrow_amount=1. | api endpoints run slowly | update existing endpoints and test them again | 2023-04-26